## Cover Page
Disability, Access & Functional Needs Emergency Planning Guidance
This planning tool has been developed to provide guidance to state and local emergency management agencies on planning for and with People with Disabilities and Others with Access and Functional Needs (PWD/AFN).
v.0515

## Table of Contents
Table of Contents | Page
Guidance Overview | 3
Executive Summary | 4
Acknowledgements Task Force Members | 5
Section A: Access & Functional Needs Position or Responsibility | 6
Section B: Community Partners/Public Engagement/Service Force Multipliers | 7, 8
Section C: Communication & Mass Notification Systems | 9
Section D: Evacuation & Transportation | 10,11,12
Section E: Mass Care | 13,14,15
Section F: Recovery | 16,17
Section G: Training & Exercises | 18
Section H: Agreements, Contracts, MOUs | 19
Website Information | 20

## Guidance Overview
Overview of the Disability, Access & Functional Needs Emergency Planning Guidance May 2015
Recent events have served to highlight the importance of planning for and with people with disabilities and others with access and functional needs (PWD/AFN) to better prepare for, respond to, and recover from, disasters. This guidance document is the product of a joint initiative between representatives of state and local emergency management agencies to provide a road map for inclusive emergency planning to be used by emergency management practitioners. The goal of this document is to make it easier to begin or enhance efforts currently underway. Instructions for Use, located in the Executive Summary, includes basic suggestions on how to begin the planning process. General information for guidance document team members is provided so emergency management planners/managers can ask questions and have access to information and ideas from the group. Development of this Guide, also located within the Executive Summary, contains resources used to create this checklist. The guidance document is divided into eight sections to help outline and focus the planning, training and exercise process, and to divide this planning guidance into separate, manageable parts. Each section is divided into tasks, a column to identify the applicable phase(s) of the emergency management cycle, the responsible lead and stakeholders for the task, and task completion status. The final column contains additional considerations or resources which may assist the planner in accomplishing that task. Finally, this guidance references a website where this document and other resources and information is housed. Recognizing the significance of disability and access and functional needs planning, the National Emergency Management Association and International Association of Emergency Managers identified this work as a joint priority.

## Executive Summary
Executive Summary
Planning for and with People with Disabilities and others with Access & Functional Needs (PWD/AFN) is an important component in the development and execution of emergency management plans, policies and procedures. Local jurisdictions need to incorporate the needs of PWD/AFN into their planning processes. State and local jurisdictions around the country are focusing on effectively incorporating the needs of PWD/AFN in community engagement efforts, emergency messaging/mass notifications, evacuations and transportation, all aspects of mass care (especially sheltering), recovery, training, exercises and in the development of agreements, contracts and MOUs. This document will assist local emergency manager practitioners with tools that will help to include, integrate and accommodate community members during all phases of the emergency management cycle. Working to address these issues at each level of government will help to improve overall efficiency, maximize resources, ensure equal access for all people and ultimately enhance nationwide emergency preparedness. In addition, this document will support whole community planning initiatives by providing tips and strategies to incorporate people with disabilities and others with access and functional needs into the framework of emergency management programs. Instructions for Use: This checklist is intended to be used as a guidance document and is not mandatory; not all items will be applicable to all jurisdictions and some items will not be in-depth enough for others. Each jurisdictions should adjust or modify this checklist depending on the needs of the community. Some information within the different checklists is redundant to ensure the different aspects of a particular task are addressed. It is the goal of the IAEM-NEMA Task Force that this checklist be used to assist emergency managers in their efforts to incorporate PWD/AFN into all emergency management phases. Getting Started: 1) Set up a conference call or face-to-face meeting with your local Mass Care Representative (s) and other emergency planning partners (i.e.: EOC Section Chiefs, PWD/AFN Agencies, Health Care Agencies, transportation, utility, caregivers agencies, etc.) 2) Review this guide together, 3) Determine which section of the guide you want to work on first and 4) Conduct a planning meeting with all these group members. Development of this Guide: This document was developed by the Joint IAEM-NEMA Disability, Access & Functional Needs Task Force. Special thanks to all Task Force members and Guidance Work Group members who participated in the development of this guidance. Resources used in the development of this guide included: the Checklist for Integrating People with Disabilities and Others with Access and Functional Needs into Emergency Preparedness, Planning, Response Recovery-Edition 2.1-2014, by June Isaacson Kailes, Associate Director, Harris Family Center for Disability and Health Policy, Western University of Health Sciences; the City of Richmond ADA Action Checklist for Emergency Management and Shelter Operations, 2005; and the FEMA Guidance on Planning for Integration of Functional Needs Support Services in General Population Shelters, 2010.

## Task Force-Guidance Work Group
IAEM/NEMA Task Force Members
State | Name | Title | Agency
Arizona | Wendy Smith-Reeve | Director | Arizona Division of Emergency Management
California | Mark Ghilarducci | Director | Governor's Office of Emergency Services
Mississippi | Robert Latham | Director | Mississippi Emergency Management Agency
Work Group Members Who Developed the Guide and Assisted in the Review
State | Name | Title | Agency
Arizona | Daniel R. Porth | Human Services Group Supervisor | Arizona Department of Emergency & Military Affairs
California | Dwight Bateman | Office of Access and Functional Needs | Governor's Office of Emergency Services
California | Grace Koch | Special Advisor | Governor's Office of Emergency Services
California | June Isaacson Kailes | Disability Policy Consultant/ Associate Director | Harris Family Center for Disability and Health Policy
California | Richard Devylder | Office of Access and Functional Needs | California Governor’s Office of Emergency Services
Connecticut | Brenda Bergeron | Division of Emergency Management and Homeland Security | CT Department of Emergency Services and Public Protection
Georgia | Angela Barton | Planning Section Manager | Georgia Emergency Management Agency
Maine | Eunice Momens | Volunteer | Maine Emergency Management Agency
Mississippi | Allison Killebrew | Senior Attorney | Mississippi Emergency Management Agency
Mississippi | Alynda Ponder | Emergency Management Coordinator | Mississippi Department of Human Services
Texas | Larry Shine | Mass Care Coordinator | Texas Division of Emergency Management Texas Homeland Security Texas Department of Public Safety

## (A) AFN Position
Section A: Access & Functional Needs Position or Responsibility
Description: This section outlines the steps for identifying a position within the emergency management chain of command responsible for coordinating preparedness planning related to people with disabilities and/or access and functional needs. Phase: Preparedness(P)/Planning (PL)/Response (RP)/Recovery (RC)/ Mitigation (M) People With Disabilities/ Access & Functional Needs: (PWD/AFN)
No. | Task | Phase | Lead/Stakeholders | Date Completed | Considerations/Resources to Complete Task
A.1 | Identify and designate an individual to serve as PWD/AFN Liaison who will be responsible for coordination of PWD/AFN activities within your jurisdiction. |  |  |  | Qualifications to include understanding of: Legal Compliance Responsibilities, Diverse PWD/AFN populations (people with vision & hearing loss, physical disabilities, speech, disability mental health disabilities, developmental and other cognitive disabilities, behavioral health issues, and issues affecting older adults), Cross-disability access issues (hearing, vision, mobility, speech, mental health and cognitive disabilities), PWD/AFN Support Service Systems (housing, benefit programs, and the variety of other resources) and Familiarity with Concepts of Universal Accessibility & Universal Design.
A.2 | Establish an PWD/AFN Task Force that will integrate the diverse needs of people with disabilities into all phases of emergency management. |  |  |  | Identify representatives from the disability community to join the PWD/AFN Task Force, i.e. disability advocates, health agencies, aging services, Transportation, Utilities, DME providers, Mass Care, EOC Section Chiefs, etc..
A.3 | Institute a message review process that includes specific steps for content review. |  |  |  | Explanation: For inclusion and appropriateness for people with disabilities and AFN, including considerations for non-English speakers.
A.4 | Identify responsibilities for PWD/AFN Liaison Position. |  |  |  | Examples of responsibilities include: 1) Serve in a permanent position in Emergency Operations Center (EOC) as a Subject Matter Expert (SME) available to advise all EOC positions (versus limited to one emergency support function (ESF) focus, individual sections, group, or unit). 2) Research and meet with other departments, agencies & jurisdiction representatives charged with similar responsibilities. 3) Provide the PWD/AFN Liaison with EM Planning Meeting dates/times/locations and encourage he/she to invite representatives from the PWD/AFN Task Force. 4) Work with the AFN Task Force to develop a AFN Framework that will provide an accurate, flexible approach to integrating access and functional needs into emergency planning, response and recovery. 5) Identify AFN Task Force members to serve on planning, training & exercise teams for each Emergency Support Function (ESF). 6) Identify PWD/AFN Task Force members to serve as liaison to government & community outreach programs. 7) Coordinate with the Public Information Officer & Joint Information Center to ensure information is accessible. 8) Compare EOPs for various city and county care facilities for vendor overlap with regard to services. 9) Create a unique checklist for PWD/AFN Liaison Position.
A.5 | Collaborate with jurisdiction’s departments and agencies to develop and integrate PWD/AFN content throughout the planning process and in each phase of the emergency coordination process. |  |  |  | Areas to integrate PWD/AFN: Emergency Plans, Annexes & Appendices, Standard Operating Procedures, Job Aids & Check List, Training & Just in Time Training, Drills & Exercises (Table Top, Functional & Full Scale), Hot Washes & After Action Reports, Agreements, Contracts, Memorandums of Understanding, Memorandums of Agreement, Emergency Preparedness Materials, PWD/AFN specific Situation Reports (SITREPS).
A.6 | Include PWD/AFN primary focus areas in the SITREPs (Situation Awareness Report/Situation Report) to keep all participants abreast of issues related to PWD/AFN. |  |  |  | Examples of focus areas: Evaluating Physical Access, Evacuation & Transportation for AFN Population, Mass Care (Sheltering, Feeding, Assistance), Behavioral/Mental Health Considerations, Recovery Activities, Public Information (creating accessible messaging), Website & Social Media (Content and Maintenance), Public Meetings (accessibility & accommodations), Community Engagement for Whole Community Planning, Logistical Considerations

## (B) Public Engagement
Section B: Community Partners/Public Engagement/Service Force Multipliers
Description: This section outlines steps and provides some guidelines for identifying and engaging community partners from the disability/access and functional needs communities to participate in emergency preparedness and planning. Emergency Management Practitioners should customize with stakeholders; those listed in this chart are examples. Phase: Preparedness(P)/Planning (PL)/Response (RP)/Recovery (RC)/ Mitigation (M) People With Disabilities/ Access & Functional Needs: (PWD/AFN)
No. | Task | Phase | Lead/Stakeholders | DATE Completed | Considerations/Resources to Complete Task
B.1 | Identify and invite qualified individuals/ representatives from the disability community to participate in the planning process. |  | PWD/AFN Liaison, PWD/AFN Task Force, CERT Team Leaders, Volunteer Organizations, Local Advocacy Groups, Functional Needs Teachers, Life Skills Teacher from High Schools |  | Examples of Representative (s) Responsibilities: •Determining effective communication methods and procedures •Identification of emerging technologies to incorporate into emergency warning systems •Review and develop education training materials •Training of government personnel regarding access and functional needs to ensure accurate training content •Training for people with disabilities on emergency preparedness •Conduct training biannually
B.2 | Identify major disabilities in the City/region and agencies/caregivers that serve them. |  | PWD/AFN Liaison, Volunteer Organizations, Local Advocacy Groups, Community Planners |  | Census Data, American Community Survey Data, Local Universities, CDC Social Vulnerability Index-http://svi.cdc.gov/
B.3 | Outreach to all PWD/AFN agencies and caregiver organizations. |  |  |  | Hold workshops, develop list of strengths & weaknesses, consider Continuity of Operations Planning (COOP) issues, areas of collaboration, community surveys, develop resource list of agencies and contacts.
B.4 | Conduct a needs assessment. |  | PWD/AFN Liaison, Volunteer Organizations, Local Advocacy Groups, Community Planners |  | Potential Sources: Other Departments/Agencies, Public Outreach, Existing Data, Geographic Information Systems
B.5 | Develop a protocol that outlines the community outreach, involvement and sustainment strategy. |  | PWD/AFN Liaison, Public Affairs Office, Volunteer Organizations, Local Advocacy Groups |  | Examples of what to include: A resource list, disability related needs, process for making advance arrangements, and how to incorporate the process into the EOP. Explanation: Network building will provide a forum for communication, coordination, cooperation and collaboration with and among disability community advocates, services organizations, the general public and emergency managers.
B.6 | Develop goals and objectives for the year, schedule quarterly meetings. |  |  |  | Consider focusing on specific planning areas for each workgroup/task force meeting, i.e.: 1) Education & Training, 2) Disaster Planning, 3) Hospital & Mass Care, 4) Site Evaluations/Shelter Operations
B.7 | Continually identify and incorporate methods to enhance community involvement. |  | PWD/AFN Liaison, Disability Advocates, Disability Organizations |  | Examples include: •Agreements/MOU’s with disability service providers •Development of a Task Force or a Committee focused on People with Disabilities •Identification of community organizations that can provide ‘just in time supplies’, like durable medical equipment (i.e. mobility devices, communication aides) •Recruitment of people with access and functional needs to participate in exercises
B.8 | Identify ways to communicate with the various disability groups in your community during the different phases of a disaster. |  | E-911 Center Representative, Private Sector Vendors, PWD/AFN Liaison, Disability Advocates, Disability Organizations, Public Information Officer |  | Consider individuals who are deaf and/or hard of hearing. Consider using IPAWS and Wireless Alert Messaging Examples of Ways to Communicate: •Develop an email list that provides awareness statements and situation reports to community partners. •Identify a specific website (s) that serves as a source of resources and tools • Use Social Media (Facebook, Twitter, Instagram, YouTube, etc.). • Phone calls • Use pictures in addition to text and voice for emergency information given •Seek out feedback from PWD/AFN community with regular testing of public warnings/alerts/ notifications (messages should be simple, clear and direct language)
Section B: Community Partners/Public Engagement/Service Force Multipliers
No. | Task | Phase | Lead/Stakeholders | Date Completed | Considerations/Resources to Complete Task
B.9 | Identify ways to conduct wellness checks on those who have self-identified as needing assistance. |  | PWD/AFN Liaison, Disability Advocates, Disability Organizations, Mass Care Representatives, Public Health Representatives, Volunteer Groups, CERT Team Leaders, Faith-Based Groups |  | Examples of individuals who may need assistance: • For individuals who are geographically isolated • For individuals who lack viable support networks • For individuals who are unable use, understand or be reached by existing alert and notification systems. • Are transportation dependent • Seniors • Non-English speaking Consider working with healthcare providers, local health organizations and housing authorities on identifying their clients who may need extra assistance.
B.10 | Work with the planning team to identify and provide mitigation assistance to the various community groups. |  |  |  | Examples include: NOAA Weather Radios with special attachments for individuals who have hearing/sight difficulties. Recruit and be prepared to accommodate individuals with access and functional needs on Community Emergency Response Teams (CERT).
B.11 | Develop a strategy (including a budget) for the use of fee based services to accommodate the needs of all team members to ensure effective participation of all team members during the planning process. |  |  |  | Examples include: • Interpreting services (language, sign language) • CART Services • Producing materials in alternative formats (braille, large print, audio) • Providing accessible transportation
B.12 | Identify potential funding opportunities that will support recruiting and contracting. |  |  |  | Include qualified representatives from diverse populations to participate in emergency planning efforts as staff, advisors, trainers, contractors and consultants.

## (C) Communication
Section C: Communication & Mass Notification Systems
Description: This section outlines the steps for identifying methods for pushing out emergency alerts/warnings/messaging to PWD/AFN's. This checklist is divided between early warning notification systems and communication/mass notification systems. Phase: Preparedness(P)/Planning (PL)/Response (RP)/Recovery (RC)/ Mitigation (M) People With Disabilities/ Access & Functional Needs: (PWD/AFN)
No. | Task | Phase | Lead/Stakeholders | Date Completed | Considerations/Resources to Complete Task
Early Warning
C.1 | Identify and develop a plan to use multiple systems to reach those with sensory/communication needs; consideration is given to those who are deaf or blind or non-English speaking. |  |  |  | Consider sending out emergency communication information directly to healthcare providers. This messaging can be specific preparedness information for providers to disseminate to their clients.
C.2 | Verify and repeat warning and informational messages for delivery. |  |  |  | Examples of Redundant Communication Options include: Announce it, Caption it, Picture it, Describe it, E-mail it, Relay it, Text it, Post it, Interpret it (language & sign), Repeat it (frequently)
C.3 | Screen all messages to ensure simplicity for those with intellectual disabilities.
C.4 | Ensure those within the disability community are involved in pre-planning methods of delivery. |  |  |  | Consider working with families, caregivers and personal support networks.
C.5 | Ensure social media sites are simple and available with captioning when videos are used. |  |  |  | Include audio description for people who are blind or visually impaired. Anything that is spoken should be captioned, and anything captioned should have verbal narration to include all audiences.
C.6 | Inform and instruct Public Information Officers on specialized public messaging delivery methods for PWD/AFN.
Communication Notification
C.7 | Develop a plan to ensure public information is given in multiple ways that meets the needs of your community. |  |  |  | i.e. to reach the right people, at the right time, at the right place with the right messages that can be understood and used. Consideration is given to those who are deaf or blind or non-English speaking. Consider working with families, caregivers and personal support networks.
C.8 | Develop a process in the EOP for obtaining resources for an effective means of communications for the Deaf and Hoh (TTY, videophones, interpreters, text messages, Sidekicks, etc.)
C.9 | Develop a process in the EOP for obtaining resources for effective means of communications for the blind or low vision (Braille, large print, assistants, etc.)
C.10 | Develop and provide prescripted email messages and group texts for/to those known in local community with communication/sensory needs.
C.11 | Ensure all public meetings contain an accommodation notice that assistive services are provided at each meeting, including, agenda and handout material in alternative formats. |  |  |  | Consider including the following statement in the meeting notice: Please contact ________ at _________ by _________to request a reasonable accommodation for the meeting.
C.12 | Ensure all video and live television coverage has captioning, ASL Interpreters and an audio description.
Evacuation Communications
C.13 | Establish interoperable channels of communication between EOC, first responders, transportation providers and building personnel.
C.14 | Establish mass evacuation notification procedures for PWD/AFN populations.
C.15 | Build notification and communication methods into EOC and provide methods to first responders and transportation providers.
C.16 | Establish a Communication Plan in the event of a power outage. |  |  |  | Consider working with families, caregivers and personal support networks. Include low tech options such as: paper and pencil, white boards with markers, solar battery chargers for laptops and cell phones.
C.17 | Ensure communication strategies are 508 compliant. |  |  |  | http://www.section508.gov/section-508-standards-guide
C.18 | Ensure communication technologies are tested at least twice a year.

## (D) Evacuation
Section D: Evacuation & Transportation
Description: This section outlines the steps for identifying transportation and evacuation resources with and for people with disabilities and/or access and functional needs. Phase: Preparedness(P)/Planning (PL)/Response (RP)/Recovery (RC)/ Mitigation (M) People With Disabilities/ Access & Functional Needs: (PWD/AFN)
No. | Task | Phase | Lead/Stakeholders | Date Completed | Considerations/Resources to Complete Task
D.1 | Identify and analyze evacuation scenarios considering PWD/AFN. |  |  |  | Consider working with families, caregivers and personal support networks.
D.2 | Ensure PWD/AFN are incorporated into the transportation and evacuation planning process. |  |  |  | Any contracts (MOAs or MOUs) made with transportation companies should include wording that the company will comply with all applicable federal, state, and county laws.
D.3 | Include evacuation procedures for PWD/AFN in the transportation annex of the EOP and/or other applicable planning documents. |  |  |  | Consider types of evacuation needs identified, residential care facilities
D.4 | Conduct outreach programs to educate PWD/AFN about personal evacuation planning.
D.5 | Identify and inventory disability transportation resources. |  |  |  | Examples: Para-transit, motor coaches, ambulances, etc.
D.6 | Identify and map community locations with concentrations of PWD/AFN. |  |  |  | Consider using the CDC Social Vulnerability Index Map(http://svi.cdc.gov/map.aspx)
D.7 | Identify and maintain current contact information for Agencies serving PWD/AFN. |  |  |  | Identify strategies to address client confidentiality considerations.
D.8 | Identify communication protocols established between EOCs, first responders and transportation providers.
D.9 | Develop and maintain communications operability between EOCs, first responders and transportation providers.
D.10 | Establish a database for evacuation alert notifications. Ensure a protocol is developed to maintain the database.
D.11 | Define clear thresholds and procedures for evacuation orders.
D.12 | Identify time estimates for executing moderate- and large-scale evacuations of PWD/AFN.
D.13 | Establish a system to mission task evacuation (transportation) resources.
D.14 | Develop a protocol for activation of transportation providers. |  |  |  | Who activates and how does alert and notification take place?
D.15 | Develop a timeline mobilization of transportation resources once tasked.
D.16 | Establish criteria for a prioritizing resources when demand exceeds availability.
D.17 | Define clear roles and responsibilities for highest elected official (s) regarding transportation and evacuation. |  |  |  | County Board of Supervisors/County Commissioners, City Council, Alderman-Consider use of Emergency Orders/Executive Orders or other forms of administrative action to allow for a broad definition of emergency vehicles to include ambulances, para-transit vehicles, motor coaches, etc.
D.18 | Define clear roles and responsibilities of your local agency/jurisdictions executive (s) regarding transportation and evacuation. |  |  |  | County Administrator, County Manager, Jurisdiction Manager, City Manager
D.19 | Define clear roles and responsibilities for emergency services/management regarding transportation and evacuation. |  |  |  | Ensure information regarding evacuation procedures get transmitted to front line employees.
D.20 | Define clear roles and responsibilities for Sheriff regarding transportation and evacuation.
Section D: Evacuation & Transportation
No. | Task | Phase | Lead/Stakeholders | Date Completed | Considerations/Resources to Complete Task
D.21 | Define clear roles and responsibilities for all stakeholders regarding transportation and evacuation of PWD/AFN. |  |  |  | Examples: Fire Services, Mass/Regional Transit, Health & Human Services, Public Information Officers, Public Works, Social Services, Air Quality, Water Resources and Faith-Based.
D.22 | Ensure transportation and evacuation roles and responsibilities for transportation agency (s) are clearly defined in the Transportation Annex to the EOP. |  |  |  | Examples: Fixed route buses, ADA mandated Paratransit Systems, Dial-a-rides, disability and senior transportation service providers, taxi systems, non-medical emergency vans/ambulances, school district transportation systems, colleges/universities transportation systems, airport car rentals, shuttle buses, vans, healthcare center vendors.
D.23 | Ensure transportation and evacuation plans for schools include PWD/AFN.
D.24 | Ensure transportation and evacuation plans for medical facilities include PWD/AFN.
D.25 | Ensure transportation and evacuation plans for elderly from congregate housing include PWD/AFN.
D.26 | Ensure transportation and evacuation plans for incarceration facilities include PWD/AFN.
D.27 | Compare EOPs for various city and county care facilities for vendor overlap with regard to services. |  |  |  | See Section A: ______________AFN Liaison Responsibilities.
D.28 | Ensure transportation evacuation plans include service animals and comfort animals. |  |  |  | Service Animals are covered by the ADA. Comfort Animals are not covered by the ADA. Policies on comfort animal vary by jurisdiction. Consult state and local laws.
D.29 | Ensure transportation evacuation plans include mobility devices and durable medical devices on transit equipment.
Evacuation
D.30 | Identify a system for persons needing transport assistance.
D.31 | Identify a system for documenting and tracking evacuees.
D.32 | Exercise tracking and recording procedures at least annually.
Transportation Staging Areas
D.33 | Designate personnel to manage transportation staging areas.
D.34 | Ensure a Traffic Plan for PWD/AFN is included in transportation annex.
D.35 | Identify transportation staging areas.
D.36 | Provide transportation stakeholders with the location of staging areas and reception centers.
D.37 | Provide accessible transportation information to PWD/AFN at transportation staging areas. |  |  |  | Examples of ways to provide Accessible Information:
D.38 | Identify and plan for individuals who may be unable to reach transportation staging areas. |  |  |  | When communicating to the general public, consider using the term "assembly points".
Evacuation Routes
D.39 | Clearly define evacuation and alternate evacuation routes. |  |  |  | Disseminate to public and media via PIO.
D.40 | Train transportation providers and first responders on evacuation routes/ alternate routes.
Section D: Evacuation & Transportation
No. | Task | Phase | Lead/Stakeholders | Date Completed | Considerations/Resources to Complete Task
D.41 | Ensure Traffic Control Points (TCPs) provide accessible communication. |  |  |  | Examples of Communication Accessibility:
D.42 | Ensure TCP system gives priority to evacuation (transit) resources. |  |  |  | Note: Evacuations for PWD/AFN should begin earlier than general public.
D.43 | Exercise evacuation protocols including PWD/AFN at least annually.
Evacuation Logistics
D.44 | Identify alternate transit/Paratransit operational facilities.
D.45 | Identify alternate power supply for transit/Paratransit.
D.46 | Identify alternate fuel supply for transit resources.
D.47 | Identify and train alternate driving and maintenance staff.
Training
D.48 | Coordinate EOP evacuation training with transportation providers for people who need specialty medical care (e.g., dialysis, nursing homes, etc.) and for residents of Adult Residential Care Homes, Domiciliary Care Homes, or group homes. |  |  |  | Including: Paratransit, school transit, taxi, shuttle and private bus
D.49 | Coordinate EOP evacuation exercises with transportation providers. |  |  |  | Including: Paratransit, school transit, taxi, shuttle and private bus
D.50 | Coordinate evacuation EOPs with Public Information Officers, Joint Information Centers and 211. |  |  |  | For more information on the 211 Service, go to: http://www.unitedway.org/our-work/2-1-1/

## (E) Mass Care
Section E: Mass Care
Description: This section outlines the steps for mass care preparedness, planning and response related to people with disabilities and/or access and functional needs. Pre-Identified Facilities include the following types: general population shelters, non-traditional shelters, medical shelters, evacuation or reception centers, disaster assistance and resource centers, mass or congregate feeding sites, points of distribution (PODs), safe refuge sites, resettlement processing centers, and decontamination sites. Phase: Preparedness(P)/Planning (PL)/Response (RP)/Recovery (RC)/ Mitigation (M) People With Disabilities/ Access & Functional Needs: (PWD/AFN)
No. | Task | Phase | Lead/Stakeholders | Date Completed | Considerations/Resources to Complete Task
E.1 | Shelter PWD/AFN, with or without the support of a care giver or personal assistant, in general population shelters.
E.2 | Reserve Medical Shelters as a scarce resource as determined by the jurisdiction. |  |  |  | (i.e. managing acute, unstable, terminal, or contagious health conditions requiring observation and ongoing treatment.)
Physical Accessibility of Facilities
E.3 | Develop shelter survey procedures which utilize the ADA Checklist for Emergency Shelters. |  |  |  | http://www.ada.gov/shleterck.htm http://www.disasterresource.org/images/partner-resources/Red-Cross-Shelter-Facility-Survey.pdf
E.4 | Include written procedures in the Local Emergency Operations Plan (LEOP) for surveying pre-identified facilities for ADA accessibility. |  |  |  | Consider local/state building codes. Consider reaching out to local architects.
E.5 | Perform surveys of all potential shelter facilities (based on needs for your agency) to ensure ADA accessibility. |  |  |  | (Street parking, walkways, ramps, passenger drop off areas, parking, paths of travel, doors and hardware, fire alarms, pull stations, fire extinguisher placement, assistive listening devices, signage, restrooms, kitchens, manual work about, showers, seating, surfaces, alarm signals (visual and audio), light fixture switch placement, water fountains and play structures.)
E.6 | Assess sites identified in the emergency plans for capacity, accessibility, and use type. (i.e. shelter, POD, etc.) |  |  |  | Capacity for PWD/AFN should be based on 40 to 60 sq. ft./pp or more if needed.
E.7 | Identify remediation actions for ADA accessibility gaps.
E.8 | Develop a facility database or matrix which includes clearly defined categories regarding degree of accessibility for each with qualifying thresholds. |  |  |  | (i.e. Readily Accessible, Minor Repairs Needed, Under Renovation, Renovation scheduled, etc.) http://www.ada.gov/shleterck.htm Refer to Matrix template.
E.9 | Develop a list of amenities and equipment required for each facility to be fully functional and accessible. |  |  |  | (i.e. portable showers, restrooms, tents, refrigerators, manual work around, quick connects, power assessments, portable generators, etc.)
E.10 | Develop a list of physical locations and attach to each annex in the emergency plan as appropriate. |  |  |  | Address and GPS coordinates
Physical Accessibility Site Set-Up and Maintenance
E.11 | Designate a coordinator to oversee functional needs services to include:
E.12 | Develop a site set-up map for each facility.
E.13 | Shelter Manager to conduct a just-in-time site walk through to ensure accessibility prior to opening the facility to public use.
Section E: Mass Care
No. | Task | Phase | Lead/Stakeholders | Date Completed | Considerations/Resources to Complete Task
E.14 | Ensure aisle widths are accessible including the paths to areas within the site. (bathrooms, feeding areas, commodities, etc.)
E.15 | Ensure restrooms are available and accessible.
E.16 | Ensure all signs are accessible in location and language.
E.17 | Ensure electricity is accessible to those with AFN.
E.18 | Ensure facility grounds and entryways are accessible. (drop off areas, parking, bathroom routes)
E.19 | Ensure sleeping areas are accessible.
E.20 | Provide Privacy/Quiet/Low Stimulation areas.
E.21 | Ensure communications equipment (phones, chargers, computers) is accessible to wheelchair, TTY, email or wireless device users.
Shelter Operation
Registration
E.22 | Ensure line management is accessible to those with access and functional needs.
E.23 | Ensure expedited access is given to those with access and functional needs. |  |  |  | Expedited access will allow shelter personnel to determine functional needs support services.
E.24 | Ensure accessibility during the Initial Intake and Follow-Up processes.
Health and Safety Issues
E.25 | Ensure plans support families staying together.
E.26 | Ensure plans include protocol & resources to request trained medical staff and volunteers.
E.27 | Develop procedures for referring people with acute medical needs in general population shelters to medical shelters or alternate facilities. |  |  |  | Alternate facilities may be hospitals or nursing homes with MOUs. Ensure accessible transportation is available.
E.28 | Ensure congregate feeding provides for dietary needs due to restrictions, food allergies or medical diagnoses. |  |  |  | Consider development of a medication protocol that would allow medication to be temporarily prescribed by a physician at a shelter.
E.29 | Ensure plans include protocol and resources for requesting personal care assistance for a dependent person when needed. |  |  |  | Consider developing a protocol for obtaining durable medical equipment consumable medical supplies and personal assistance services.
E.30 | Ensure plans allow persons with medical needs access to food and beverages as needed.
E.31 | Ensure plans include protocol and resources for assistance with service animals accompanying persons with disabilities. (i.e. feeding, hygiene, exercising animals, etc.).
E.32 | Assess facilities for accessibility barriers several times daily.
Communications Access
E.33 | Utilize multiple communication methods. |  |  |  | (i.e. announce, post, caption, picture, email, text, interpret in language & sign, etc.) Consider using graphics in signs to address all types of communication needs (LEP, ASL, illiteracy, limited comprehension).
E.34 | Provide transportation information.
E.35 | Repeat communication frequently. |  |  |  | Various modes of communication (verbal, text, graphics, pictures, ASL).
E.36 | Develop procedures for reporting and resolving unmet needs.
Section E: Mass Care
No. | Task | Phase | Lead/Stakeholders | Date Completed | Considerations/Resources to Complete Task
E.37 | Develop procedures for obtaining resources for effective means of communications for the Deaf. (TTY, videophones, interpreters, text messages, Sidekicks, etc.) |  |  |  | ASL Interpreter Services, Skype, FEMA Resources
E.38 | Develop procedures for obtaining resources for printed materials in accessible formats (Braille, large print, e-mail, graphics, pictures).
E.39 | Develop procedures for obtaining resources for effective means of communications for non-English speaking persons.
E.40 | Develop procedures for obtaining durable medical equipment, consumable medical supplies, and other unmet functional needs support services.
Decontamination
E.41 | Decontaminate assistive technology devices, DME including mobility and speech generating devices, and service animals.
E.42 | Develop procedures for decontaminating assistive technology devices and equipment or refer to existing procedures.
E.43 | Develop procedures for replacing equipment and/or services to people with access and functional needs.
E.44 | Train staff on decontamination procedures of assistive technology devices and equipment or how to request decontamination teams, if available.
E.45 | Decontamination of Service Animals and pets.
E.46 | Develop procedures for decontaminating service animals or refer to existing procedures.
E.47 | Train personnel in decontamination procedures for service animals or how to request decontamination teams, if available.
Sheltering In Place
E.48 | Develop plans to ensure continued delivery of services, especially with regard to Restricted Points of Entry or Access Control Points (ACPs) to include: |  |  |  | Access Control Points: A location staffed to restrict entry of unauthorized personnel into a risk area during emergency and/or disaster events. Access control is normally performed just outside of the risk area and involves use of vehicles, barricades, or other measures to deny access to a particular area.
E.49 | Ensure coordination with Law Enforcement
E.50 | Ensure ACP access for home health services and personal attendants.
E.51 | Ensure ACP access for home delivered meals.
E.52 | Ensure ACP access for proxy pick up and delivery of supplies, oxygen, food, medications, etc. |  |  |  | Another consideration: replenishing food, water and supplies for service animals and pets. If the person cannot get out, they still need to take care of the animal.
E.53 | Develop a feeding plan for citizens required to shelter-in-place for extended periods or refer to previously developed Feeding Plan.
Life Safety Wellness Checks
E.54 | Perform Life Safety Wellness Checks if appropriate.
E.55 | Develop a list of triggers for performing Life-Safety/Wellness Checks. (i.e. Shelter-in-Place duration of 3 days or more, sustained power outages, etc.) |  |  |  | Another consideration: After 1-2 days, people on dialysis will need to get to a dialysis center for medical treatment.
E.56 | Develop procedures for evaluating and reporting unmet needs. (i.e. Who, what, when, how, etc.)
E.57 | Develop procedures for requesting items, supplies, or equipment to resolve unmet needs.

## (F) Recovery
Section F: Recovery
Description: This section outlines considerations and guidelines for planning with and for PWD/AFN during the recovery phase of an emergency or disaster. Phase: Preparedness(P)/Planning (PL)/Response (RP)/Recovery (RC)/ Mitigation (M) People With Disabilities/ Access & Functional Needs: (PWD/AFN)
No. | Task | Phase | Lead/Stakeholders | Date Completed | Considerations/Resources to Complete Task
F.1 | Identify a process for integrating the PWD/AFN community into the short- and long-term recovery planning and efforts. |  |  |  | AFN Task Force referred to in Section A.
a) Coordinate with stakeholders on the delivery of recovery services.
| b) Collaborate Case Management with community partners. |  |  |  | independent living, developmental disability, aging, family and faith-based, culture-specific, services, etc..
| c) Identify ways to repair and/or replace durable medical equipment and housing resources for activities of daily living. |  |  |  | Items such as: wheelchairs, walkers, canes, ramps, grab bars, bathrooms fixtures, etc.
| d) Reinforce FEMA's Individual Assistance grants for federally declared disasters. |  |  |  | Funds can be used for items such as: wheelchairs, scooters, battery chargers, hearing aids, computers, kitchen & bathroom access alterations, widening doorways, ramps, etc.
F.2 | Ensure Disaster Recovery Center (DRC)assistance centers have universal accessibility. |  |  |  | Recovery Centers also referred to as: Individual Assistance Service Centers (IASC), Multi-Agency Resource Centers (MARC)
F.3 | Ensure PWD/AFN population have access to all services and programs offered at DRC's. |  |  |  | Consider providing the FEMA Disaster Assistance website (disasterassistance.gov) and/or the disaster assistance number (1-800-621-FEMA (3362) (hearing/speech impaired ONLY-Call TTY: 1-800-462-7585) to apply for services. Face Time, Skype, Video Relay/Remote Interpreting.
F.4 | Ensure equal access for application assistance. |  |  |  | Examples include: line management, phone, website, assistive technology, ASL interpreters, home visits, large print materials, Braille, CD, electronic, audio, etc.
F.5 | Ensure materials and forms are included in various alternate formats. |  |  |  | Large print, braille, CD, Electronic, Audio, Sign Language,
F.6 | Disseminate service information using multiple communication methods. |  |  |  | Radio, TV, internet, fact sheets, posters, social media, etc.
F.7 | Prioritize essential services restoration for PWD/AFN (electricity, debris removal, water, mass transit, health services).
F.8 | Develop protocols for allowing Personal Assistant Services (PAS) providers and care-givers access re-entry point access.
F.9 | Identify accessible temporary and permanent housing resources. |  |  |  | State Housing Portals: housing search website, FEMA Housing Portal, HUD Housing Portal, USDA Housing Portal
Re-entry
F.10 | Establish a communication protocol for notifying PWD/AFN evacuees of re-entry.
F.11 | Ensure the transportation plan includes assistance for PWD/AFN for returning home.
Section F: Recovery
No. | Task | Phase | Lead/Stakeholders | Date Complete (Y/N) | Considerations/Resources to Complete Task
Demobilization
F.12 | Establish timeline to demobilize transportation resources.
F.13 | Establish a procedure to check-out emergency evacuation resources.
F.14 | Establish procedures to debrief demobilizing personnel.
F.15 | Establish procedures to debrief evacuees.
F.16 | Review demobilization procedures at least annually. |  |  |  | Refer to LEOP (Local Emergency Operations Plan).
After Action Review and Reporting
F.17 | Establish a process for after action assessment and reporting. |  |  |  | Refer to LEOP.
F.18 | Integrate evacuation, transportation and communication After Action Report (AAR) findings into AARs for EOC, field staff and transportation providers. |  |  |  | Refer to LEOP.
F.19 | Establish a process to implement after action changes. |  |  |  | Refer to LEOP.
F.20 | Establish a process for training staff on after action changes. |  |  |  | Refer to LEOP.

## (G) Training
Section G: Training & Exercises
Description: This section provides guidelines for incorporating considerations regarding people with disabilities and others with access and functional needs into training and exercise programs. Phase: Preparedness (P)/Planning (PL)/Response (RP)/Recovery (RC)/ Mitigation (M) People With Disabilities/ Access & Functional Needs: (PWD/AFN)
No. | Task | Phase | Lead/Stakeholders | Date Completed | Considerations/Resources to Complete Task
G.1 | Develop plan to include elements related to the disability community in all exercises, whether discussion or operation based (seminars, tabletops, functional, drills, full scale). |  |  |  | Refer to XXXXX LA COUNTY's XXX document found at ____________________
G.2 | Implement a plan to use individuals with disabilities and others with access and functional needs in all levels of training and exercises, to be included in training/exercise development, exercise committee, players, exercise controllers and evaluators.
G.3 | Ensure training programs provide accommodations for those with functional and access needs to attend the training. |  |  |  | Accommodations may include: auxiliary aids and services such as ASL interpreters, captioners, print material in alternate formats
G.4 | Ensure all training programs address special considerations to providing information about providing equal access to persons within the disability community, including Personal Care Assistants.
G.5 | Train essential staff on evacuation plan.
G.6 | Conduct training and exercises on use of assets. |  |  |  | Include information obtained from the AAR. See Section F.
G.7 | Ensure all service providers/personnel have basic ICS/NIMS training. |  |  |  | Include additional training requirements.
G.8 | Ensure essential service providers and staff are aware of family emergency planning tips.
G.9 | Identify and train all (scheduled and back up) drivers on how to use accessibility features of vehicle and how to the secure the passenger in the wheelchair to the vehicle.
Exercises
G.10 | Integrate all providers such as transit, Paratransit, schools and other transportation agencies into tabletop exercises.
G.11 | Functional evacuation exercises have been conducted integrating all providers such as transit, para-transit, schools and other transportation agencies.
G.12 | Include providers and passengers with disabilities into full-scale evacuation exercises.
G.13 | Include real PWD/AFN in various exercises with other participants.

## (H) Agreements
Section H: Agreements, Contracts, MOUs
Description: This section provides guidelines and strategies for inclusion of PWD/AFN into emergency management programs through more formalized agreements like contracts, Memorandums of Agreement (MOA) and Memorandums of Understanding (MOU). Phase: Preparedness(P)/Planning (PL)/Response (RP)/Recovery (RC)/ Mitigation (M) People With Disabilities/Access & Functional Needs: (PWD/AFN)
No. | Task | Phase | Lead/Stakeholders | Date Completed | Considerations/Resources to Complete Task
H.1 | Ensure all contracts have language that the contractor/vendor will comply with all applicable federal, state and county laws, including the ADA for all services
H.2 | Ensure contracts, agreements, MOUs, etc. are in place for durable medical goods and personal assistance services for shelters, feeding, showers, port-a-potties.
H.3 | Provide equal access to programs and services for everyone, including PWD/AFN.
H.4 | Consider having PWD/AFN review agreements, contracts and MOUs to ensure services are accessible for the whole community.
MOUs/MOAs
H.5 | Establish written agreements between local government and transportation, utility, health care, DME providers which includes activation and notification procedures, how assets will be deployed and plan for regular updates
H.6 | Establish written agreements with transportation agencies within jurisdiction and neighboring jurisdiction.
H.7 | Establish written agreements with local and out of state interpreter referral agencies for in-person and video remote interpreting. |  |  |  | For any area with dialects and different languages used on a daily basis, consider using local agencies first and then other agencies who have interpreters who have lived in the community before and know local terminology and names of places.
H.8 | Establish contingency contracts for sign language interpreters. |  |  |  | Consider working with the local interpreter groups and agencies to develop a rapport. Expectations related to knowing emergency terminology and payment may be different on both sides. Discuss options and develop appropriate training prior to establishing contracts with sign language interpreters.
H.9 | Ensure contingency contracts exist with private sector transportation companies. |  |  |  | Ensure private transportation companies used as contractors have accessible vehicles.
H.10 | Consider utilizing EMAC resources to augment service needs if necessary.
Cost Tracking and Reporting Procedures
H.11 | Identify a system for tracking hours and cost for stakeholders/partners.
H.12 | Practice emergency cost tracking procedures at least annually.

## Website Information
Website Information
***Website under development; links will be inserted here when website information becomes available.